## Bug_Tracking
Bug # | Status | Raised By | Tested on Version | Test Case Id | Step to Reproduce | Expected Results | Actual Results | Screen Shot | Re-testing (Result) | Re-testing v2 (Scree-shot) | Priority | Severity
BR_1 | Close | Bijaya | V1 | NC_4 | • Enter blank space in first character in NAME field | An error message : Name cannot have space in first character in NAME Field | Wrong error message. |  | As expected |  | Medium | Medium
BR_2 | Close | Bijaya | V1 | NC_5 | • Do not enter the anything in ADDRESS field • Fill up the other remaining field and save the data. | An error message : Address must not be blank. | No error message. |  | As expected |  | Medium | Medium
BR_3 | Close | Bijaya | V1 | NC_6 | • Enter space in the first character in ADDRESS field | An error message : First character in ADDRESS field cannot have space. | No error message |  | As expected |  | Medium | Medium
BR_4 | Close | Bijaya | V1 | NC_7 | • Enter the special character in ADDRESS field | An error message : Special characters are not allowed in ADDRESS field. | No error message |  | As expected |  | Medium | Medium
BR_5 | Close | Bijaya | V1 | NC_23 | • Enter the space in the first character | An error message : First character in TELEPHONE NUMBER field cannot have space. | No error message. |  | As expected |  | Medium | Medium
BR_6 | Close | Bijaya | V1 | NC_26 | • Enter the space in the first character | An error message : First character can not have space | No error message. |  | As expected |  | Medium | Medium
BR_7 | Close | Bijaya | V1 | EC_4 | • Enter the space in the first character CUSTOMER ID field. | An error message : Space in the first character are not allowed. | No error message shown. |  | As expected |  | Medium | Medium
BR_8 | Close | Bijaya | V1 | EC_5 | • Do not enter the anything in ADDRESS field • Fill up the other remaining field and save the data. | An error message : Please enter the address in ADDRESS field. | Connection error is shown | N/A | As expected |  | High | High
BR_9 | Close | Bijaya | V1 | EC_6 | • Enter space in the first character in ADDRESS field | An error message : First character in ADDRESS field cannot have space. | Connection error is shown | N/A | As expected |  | High | High
BR_10 | Close | Bijaya | V1 | EC_7 | • Enter the special character in ADDRESS field | An error message : Special characters are not allowed in ADDRESS field. | Connection error is shown | N/A | As expected |  | High | High
BR_11 | Close | Bijaya | V1 | EC_8 | • Enter the special character in CITY field | An error message : Special characters are not allowed in CITY field | Connection error is shown | N/A | As expected |  | High | High
BR_12 | Close | Bijaya | V1 | EC_9 | • Do not enter any thing in CITY field • Fill up the other field and save the data. | An error message : City field must not be blank. | Connection error is shown | N/A | As expected |  | High | High
BR_13 | Close | Bijaya | V1 | EC_10 | • Enter the numbers in CITY field | An error message : Numbers are not allowed in CITY field | Connection error is shown | N/A | As expected |  | High | High
BR_14 | Close | Bijaya | V1 | EC_11 | • Enter space in the first character in CITY field | An error message : Space in the first character are not allowed. | Connection error is shown | N/A | As expected |  | High | High
BR_15 | Close | Bijaya | V1 | EC_12 | • Enter the numbers in STATE field | An error message : Numbers are not allowed in STATE field | Connection error is shown | N/A | As expected |  | High | High
BR_16 | Close | Bijaya | V1 | EC_13 | • Do not enter any thing in STATE field • Fill up the other field and save the data. | An error message : Please enter the name in STATE field. | Connection error is shown | N/A | As expected |  | High | High
BR_17 | Close | Bijaya | V1 | EC_14 | • Enter the special characters in STATE field | An error message : Special characters are not allowed in STATE field. | Connection error is shown | N/A | As expected |  | High | High
BR_18 | Close | Bijaya | V1 | EC_15 | • Enter blank space in first character in STATE field | An error message : State must not be blank. | Connection error is shown | N/A | As expected |  | High | High
BR_19 | Close | Bijaya | V1 | EC_16 | • Enter the characters in PIN CODE field | An error message : Characters are not allowed in | Connection error is shown | N/A | As expected |  | High | High
BR_20 | Close | Bijaya | V1 | EC_17 | • Do not enter any thing in PIN CODE field • Fill up the other field and save the data. | An error message : Please enter the pin code in PIN CODE field. | Connection error is shown | N/A | As expected |  | High | High
BR_21 | Close | Bijaya | V1 | EC_18 | • Enter the special characters in NAME field | An error message : Special characters are not allowed in PIN CODE field. | Connection error is shown | N/A | As expected |  | High | High
BR_22 | Close | Bijaya | V1 | EC_19 | • Enter the code less than 6 Digits. • Enter the code exactly 6 Digits. • Enter the code more than 6 Digits. | • An error message : PIN code should be exactly six digits. • No message • An error message : PIN code should be exactly six digits. | Connection error is shown | N/A | As expected |  | High | High
BR_23 | Close | Bijaya | V1 | EC_20 | • Enter the space in the first character | An error message : Special characters are not allowed in PIN CODE field. | Connection error is shown | N/A | As expected |  | High | High
BR_24 | Close | Bijaya | V1 | EC_21 | • Do not enter the anything in TELEPHONE NUMBER field • Fill up the other remaining field and save the data." | An error message : Please enter the mobile number if TELEPHONE NUMBER field. | Connection error is shown | N/A | As expected |  | High | High
BR_25 | Close | Bijaya | V1 | EC_22 | • Enter the special characters in TELEPHONE NUMBER field | An error message : Special characters are not allowed in TELEPHONE NUMBER field. | Connection error is shown | N/A | As expected |  | High | High
BR_26 | Close | Bijaya | V1 | EC_23 | • Enter the characters in TELEPHONE NUMBER field | An error message : Characters are not allowed in TELEPHONE NUMBER field. | Connection error is shown | N/A | As expected |  | High | High
BR_27 | Close | Bijaya | V1 | EC_24 | • Enter the space in the first character | An error message : First character in TELEPHONE NUMBER field cannot have space. | Connection error is shown | N/A | As expected |  | High | High
BR_28 | Close | Bijaya | V1 | EC_25 | • Do not enter any thing in EMAIL ID field • Fill up the other field and save the data. | An error message : Please enter the mobile number if EMAIL ID field. | Connection error is shown | N/A | As expected |  | High | High
BR_29 | Close | Bijaya | V1 | EC_26 | • Enter the email id with invalid format (Without @, and other valid format) | An error message : Please enter the valid email id. | Connection error is shown | N/A | As expected |  | High | High
BR_30 | Close | Bijaya | V1 | EC_27 | • Enter the space in the first character | An error message : First character in TELEPHONE NUMBER field cannot have space. | Connection error is shown | N/A | As expected |  | High | High
BR_31 | Close | Bijaya | V1 | NA_1 | • Do not enter the customer id CUSTOMER ID field. • Enter the other field and save the data. | • An error message : Customer id must not be blank. | No error message. |  | As expected |  | Medium | Medium
BR_32 | Close | Bijaya | V1 | NA_2 | • Enter the special characters in CUSTOMER ID field. | • An error message : Special characters are not allowed. | No error message. |  | As expected |  | Medium | Medium
BR_33 | Close | Bijaya | V1 | NA_3 | • Enter the characters in CUSTOMER ID field. | • An error message : Characters are not allowed. | No error message. |  | As expected |  | Medium | Medium
BR_34 | Close | Bijaya | V1 | NA_4 | • Enter space in the first charcter of CUSTOMER ID field. | • An error message : First character cannot have space. | No error message. |  | As expected |  | Medium | Medium
BR_35 | Close | Bijaya | V1 | NA_5 | 1) Do not enter a value in Initial Deposit Field 2) Press TAB and move to next Field | An error message "Initial deposit cannot be empty" must be shown | No error message is shown |  | As expected |  | Medium | Medium
BR_36 | Close | Bijaya | V1 | NA_6 | 1) Enter character value in Initial Deposit Field | An error message "Initial Deposit must be numeric" must be shown | No error message is shown |  | As expected |  | Medium | Medium
BR_37 | Close | Bijaya | V1 | NA_7 | 1) Enter Special Character In Initial Deposit Field | An error message "Initial Deposit cannot have special character" must be shown | No error message is shown |  | As expected |  | Medium | Medium
BR_38 | Close | Bijaya | V1 | NA_8 | 1) Initial Deposit cannot have Blank space 2) Press Tab | An error message "Initial Deposit cannot have blank space" must be shown | No error message is shown |  | As expected |  | Medium | Medium
BR_39 | Close | Bijaya | V1 | NA_9 | 1) Enter first character space 2) Press Tab | An error message "Initial Deposit cannot have first character space" must be shown | No error message is shown |  | As expected |  | Medium | Medium
BR_40 | Close | Bijaya | V1 | EA_4 | 1) Do not enter a value in Customer id Field 2) Press TAB and move to next Field | An error message "Customer id cannot be empty" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_41 | Close | Bijaya | V1 | EA_5 | 1) Enter character value in Customer id Field | An error message "Customer id must be numeric" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_42 | Close | Bijaya | V1 | EA_6 | 1) Enter Special Character In Customer id Field | An error message "Customer id cannot have special character" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_43 | Close | Bijaya | V1 | EA_7 | 1) Customer Id cannot have Blank space 2) Press Tab | An error message "Customer id cannot have blank space" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_44 | Close | Bijaya | V1 | EA_8 | 1) Enter first character space 2) Press Tab | An error message "Customer id cannot have first character space" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_45 | Close | Bijaya | V1 | EA_9 | 1) Do not enter a value in Balance Field 2) Press TAB and move to next Field | An error message "Balance cannot be empty" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_46 | Close | Bijaya | V1 | EA_10 | 1) Enter character value in Balance Field | An error message "Balance must be numeric" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_47 | Close | Bijaya | V1 | EA_11 | 1) Enter Special Character In Balance Field | An error message "Balance cannot have special character" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_48 | Close | Bijaya | V1 | EA_12 | 1) Balance cannot have Blank space 2) Press Tab | An error message "Balance cannot have blank space" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_49 | Close | Bijaya | V1 | EA_13 | 1) Enter first character space 2) Press Tab | An error message "Balance cannot have first character space" must be shown | Cannot be executed due to connection issue | N/A | As expected |  | High | High
BR_50 | Close | Bijaya | V1 | DC_4 | 1) Enter space in the first charcter of CUSTOMER ID field. | • An error message : Space in the first character of CUSTOMER ID field is not allowed. | No error message shown. |  | As expected |  | Medium | Medium
BR_51 | Close | Bijaya | V1 | CS_4 | • Enter the special character in Amount Lower Limit field. | • An error message : Special characters are not allowed in Amount Lower Limit Field | No error message shown. |  | As expected |  | Medium | Medium
BR_52 | Open | Bijaya | V1 | CS_5 | • Do not enter anything in Amount Lower Limit field • Fill up the other field and submit the data. | • An error message : Amount lower limit cannot be blank. | No error message shown. |  | Same Error |  | Medium | Medium
BR_53 | Close | Bijaya | V1 | CS_6 | • Enter the character in Amount Lower Field. | • An error message : Character are not allowed in Amount Lower Field. | No error message shown. |  | As expected |  | Medium | Medium
BR_54 | Close | Bijaya | V1 | CS_7 | • Enter the special character in Number of Transaction Field | • An error message : Special characters are not allowed in Number of Transcation Field | No error message shown. |  | As expected |  | Medium | Medium
BR_55 | Open | Bijaya | V1 | CS_8 | • Do not enter anything in Number of transcation field • Fill up the other field and submit the data. | • An error message : Number of transcaction must not be blank | No error message shown. |  | Same Error | Same error | Medium | Medium
BR_56 | Close | Bijaya | V1 | CS_9 | • Enter the character in Number of Transcation Field | • An error message : Character are not allowed in Number of transaction field. | No error message shown. |  | As expected |  | Medium | Medium
BR_57 | Close | Bijaya | V1 | IP_1 | 1) Login to the application 2) Click "New Customer" 3) Fill up the details : • Customer Name • Gender • Date of Birth • Address • City • State • PIN • Telephone Number • E-Mail | Registration sucessful. New Customer Added | Error Message. Could not connect: Access denied for user 'root'@'localhost' (using password: NO) |  | As expected |  | Medium | Medium
BR_58 | Close | Bijaya | V1 | Ip_2 | 1) Login to the application 2) Click "New Customer" 3) Fill up the details : • Customer Name • Gender • Date of Birth • Address • City • State • PIN • Telephone Number • E-Mail 5) Click the "submit/save" button | Email Id already exist. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_59 | Close | Bijaya | V1 | IP_3 | 1) Login to the application 2) Click "Edit Customer" 3) Edit the details : • Customer Name • Gender • Date of Birth • Address • City • State • PIN • Telephone Number • E-Mail 5) Click the "submit/save" button | Records Updated Sucessfully . | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_60 | Open | Bijaya | V1 | IP_4 | 1) Login to the application 2) Click "Edit Customer" 3) Enter the valid customer id. 4) Edit the details : • Customer Name • Gender • Date of Birth • Address • City • State • PIN • Telephone Number • E-Mail 5) Click the "submit/save" button | Email Id already exist. | Cannot be executed due to connection issue | N/A | Different customer with same email id is being able to be register |  | High | High
BR_61 | Open | Bijaya | V1 | !P_5 | 1) Login to the application 2) Click "Edit Customer" 3) Enter the invalid customer number | Error message : Invalid customer id | Cannot be executed due to connection issue | N/A | Wrong error message. |  | Medium | Medium
BR_62 | Close | Bijaya | V1 | !P_6 | 1) Login to the application. 2) Click "Edit Customer" 3) Enter the valid but not associated customer id with the logged in Manager. | Customer is not asscociated. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_63 | Close | Bijaya | V1 | IP_7 | 1) Login to the application using valid credentials. 2) Click "New Account" 3) Fill up the details : ● Customer Id ● Account Type ● Initial deposit 4) Click the "submit" button | New"account type" account added sucessfully. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_64 | Close | Bijaya | V1 | IP_8 | 1) Login to the application using valid credentials. 2) Click "Saving" Account 3) Fill up the details : ● Customer Id ● Saving account ● Initial deposit 4) Click the "submit" button | New "saving" account added succesfully. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_65 | Close | Bijaya | V1 | IP_9 | 1) Login to the application using valid credentials. 2) Click "New" Account 3) Fill up the details : ● Customer Id ● Current Account ● Initial deposit 4) Click the "submit" button | New "current" account added successfully. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_66 | Close | Bijaya | V1 | IP_10 | 1) Login to the application using valid credentails. 2) Click "New Account". 3) Fill up the details in the form: ● Customer Id ● Saving Account ● Initial deposit 4) Click the "submit" button | New "saving" account added succesfully. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_67 | Close | Bijaya | V1 | IP_11 | 1) Login to the application using valid credentails. 2) Click "New Account". 3) Fill up the details in the form: ● Customer Id ● Current Account ● Initial deposit 4) Click the "submit" button | New "current" account added succesfully. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_68 | Open | Bijaya | V1 | IP_12 | 1) Login to the application using valid credentails. 2) Click "New Account". 3) Fill up the details in the form: ● Customer Id ● Current Account ● Initial deposit 4) Click the "submit" button | Error :Invalid customer id. | Cannot be executed due to connection issue | N/A | Wrong error message. |  | Medium | Medium
BR_69 | Close | Bijaya | V1 | IP_13 | 1) Login to the application using valid credentails. 2) Click "New Account". 3) Fill up the details in the form: ● Customer Id ● Current Account ● Initial deposit 4) Click the "submit" button | Error : Initial deposit must be greater than 500 | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_70 | Close | Bijaya | V1 | IP_14 | 1) Login to the application using valid credentails. 2) Click "New Account". 3) Fill up the details in the form: ● Customer Id ● Current Account ● Initial deposit 4) Click the "submit" button | Error : Customer id is not associated | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_71 | Open | Bijaya | V1 | IP_15 | 1) Login to the application using valid credentails. 2) Click "Edit Account". 3) Fill up the details in the form: ● Customer Id ● Current Account ● Initial deposit 4) Click the "submit" button | Record updated successfully. | Cannot be executed due to connection issue | N/A | SRS document does not specigy which fields are editbale. Here, customer id and balance are not editbale. |  | Medium | Medium
BR_72 | Close | Bijaya | V1 | IP_16 | 1) Login to the application using valid credentails. 2) Click "Edit Account". 3) Enter the invalid "Account No". 4) Click "submit" button. | Error message : Invalid account No | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_73 | Close | Bijaya | V1 | IP_17 | 1) Login to the application using valid credentails. 2) Click "Edit Account". 3) Enter the valid "Account No" 4) Click "submit" button. | Error message : Account no not associated. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_74 | Close | Bijaya | V1 | IP_18 | 1) Login to the application with valid credentials 2) Click "Delete Account". 3) Enter the valid account no. 4) Click "submit" button | Successfully deleted. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_75 | Open | Bijaya | V1 | IP_19 | 1) Login to the application with valid credentials 2) Click "Delete Account". 3) Enter the invalid account no. 4) Click "submit" button | Error message : Enter the valid account no | Cannot be executed due to connection issue | N/A | Error message : Account could not be deleted. |  | Medium | Medium
BR_76 | Open | Bijaya | V1 | IP_20 | 1) Login to the application with valid credentials 2) Click "Delete Account". 3) Enter the valid account no. 4) Click "submit" button | Error message : Account no not associated with logged in manager | Cannot be executed due to connection issue | N/A | Error message : Account could not be deleted. |  | Medium | Medium
BR_77 | Close | Bijaya | V1 | IP_21 | 1) Login to the application with valid credentials. 2) Click "Delete" customer 3) Enter the customer id 4) Click the "Submit" button. | Error message : Customer with active account cannot be deleted. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_78 | Open | Bijaya | V1 | IP_22 | 1) Login to the application with valid credentials. 2) Click "Delete" customer 3) Enter the customer id 4) Click the "Submit" button. | Successfully deleted customer. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_79 | Open | Bijaya | V1 | IP_23 | 1) Login to the application with valid credentials. 2) Click "Delete" customer 3) Enter the customer id 4) Click the "Submit" button. | Error message : Invalid customer id | Cannot be executed due to connection issue | N/A | Wrong error message : Account does not exist |  | Medium | Medium
BR_80 | Close | Bijaya | V1 | IP_24 | 1) Login to the application with valid credentials. 2) Click "Delete" customer 3) Enter the customer id 4) Click the "Submit" button. | Error message : Customer not associated. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_81 | Open | Bijaya | V1 | IP_25 | 1) Login to the application with valid credentials 2) Click "Mini Statement". 3) Enter the account no. 4) Click the "Submit" button. | Show last 5 transcations. | Cannot be executed due to connection issue | N/A | Error : Module does not provide any functionalities to make a transaction. Hence, test case fail to be execute. | N/A | Medium | Medium
BR_82 | Open | Bijaya | V1 | IP_26 | 1) Login to the application with valid credentials 2) Click "Mini Statement". 3) Enter the account no. 4) Click the "Submit" button. | Show last 5 transcations of both customer | Cannot be executed due to connection issue | N/A | Error : Module does not provide any functionalities to make a transaction. Hence, test case fail to be execute. | N/A | Medium | Medium
BR_83 | Open | Bijaya | V1 | IP_27 | 1) Login to the application with valid credentials 2) Click "Mini Statement". 3) Enter the invalid account no. 4) Click the "Submit" button. | Error message : Invalid account No | Cannot be executed due to connection issue | N/A | Wrong error message : Account does not exsit |  | Medium | Medium
BR_84 | Open | Bijaya | V1 | IP_28 | 1) Login to the application with valid credentials 2) Click "Mini Statement". 3) Enter the valid account no. 4) Click the "Submit" button. | Error message : No transaction made | Cannot be executed due to connection issue | Could not be execute because module does not provide any functionality to make transaction. | Could not be execute because module does not provide any functionality to make transaction. | N/A | Medium | Medium
BR_85 | Close | Bijaya | V1 | IP_29 | 1) Login to the application with valid credentials 2) Click "Mini Statement". 3) Enter the valid account no but not associated with the manager. 4) Click the "Submit" button. | Error message : Account not associated with manager | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_86 | Close | Bijaya | V1 | IP_30 | 1) Login to the system with valid credentials 2) Click "Customized Statement" 3) Enter the details : ● Account No ● From Date ● To Date ● Amount Lower Limit ● Number Of Transaction 4) Click "Submit" button | Display customized statement of two customers seperately. | Cannot be executed due to connection issue | N/A | As expected |  | Medium | Medium
BR_87 | Open | Bijaya | V1 | IP_31 | 1) Login to the system with valid credentials 2) Click "Customized Statement" 3) Enter the details : ● Account No ● From Date ● To Date ● Amount Lower Limit ● Number Of Transaction 4) Click "Submit" button | Error message : Invalid account No | Cannot be executed due to connection issue | N/A | Wrong error message : You are not authorized to delete this account. |  | Medium | Medium
BR_88 | Open | Bijaya | V1 | IP_32 | 1) Login to the system with valid credentials 2) Click "Customized Statement" 3) Enter the details : ● Account No ● From Date ● To Date ● Amount Lower Limit ● Number Of Transaction 4) Click "Submit" button | Error message : From date must be smaller than To Date | Cannot be executed due to connection issue | N/A | Error : System allows to enter "From date" greater than "To" date. |  | Medium | Medium
BR_89 | Close | Bijaya | V1 | Exploratory | While surfing | Guru99 Banking | Cannot be executed due to connection issue |  | As expected |  | Medium | Medium